## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Beginning | 3 | 2023-03-08 | I use npm to create the project, configure Pinia, and configure the router.
Mobile First | 10 | 2023-03-09 | I learn in one of my online courses that is better begin with mobile first, that is why I started with the implementation of the mobile design (Including about page). | 5
Desktop Responsive | 4 | 2023-03-11 | I fixed the design to work in desktop version
User story 1 | 1 | 2023-03-11 | I create a Header state to manage the title of each page
User story 2 | 2 | 2023-03-11 | Create the connection with Axios to the API through the 8080 port and show the data using props
User story 3 | 3 | 2023-03-12 | I create a filter by zip code
User story 4 | 2 | 2023-03-12 | I sort the listing by price and size switching a button
User story 5 | 4 | 2023-03-13 | I had issues with the the detail page of the mobile version because of the background’s imagen position
User story 6 | 7 | 2023-04-04 | I spent a lot of time trying different validation libraries without results until I found Zod, took me a while to understand it and I did into three big steps, 1. Create the form without validations, 2. Add form’s validations, 3. the last of the steps was dealing with the image validation and upload that I found difficult.
User story 7 | 1 | 2023-04-05 | Show and hide making usage of the VUE directive “v-if” and the router, nothing complex
User story 9 |  | 2023-04-05 | I did this User story without troubles
User story 8 | 5 | 2023-04-11 | I put a lot effort into the editing part because I did lifting in a new way that I never did before It was challenging, I researched too much to learn how to make the form reusable.
UI | 2 | 2023-04-26 | Fixed all the UI items
Format | 3 | 2023-05-04 | Fixed all the Format items
Structure | 3 | 2023-05-01 | Fixed all the Structure items
Logic | 8 | 2023-05-03 | Fixed the Logic items (missing the one related with additional data, more info requested via email)
Total amount of hours | 58